## Capital Projects Report
|  |  | 2012-07-27 |  | Prepared By Public Works Department - Engineering Division
Primary Council District | Project | Scope | Budget | Contact | June and July Activities | August Planned Activities
PROJECTS UNDER CONSTRUCTION
2 | Sidewalks In Need of Repair 38 - 2011 | To maintain a safe walking surface for the citizens of Peoria. | 250000 | Stephen Letsky | Construction was complete by 7/18/12. Final pay estimate is being prepared. | Project will be complete by Mid August.
3, 4, 5 | Northmoor - Knoxville to Sheridan (Stage 3) | Construct Northmoor with three lanes, curbs, and sidewalks/bike paths between Knoxville and Sheridan. This is an ARRA Stimulus Project | 2391543 | Scott Reeise | Working with contractor on agreement to final quantities. Project is complete and paperwork still is needed to be turned over to IDOT. | Project should be finaled out in August or September.
5 | Wilhelm Bridge | Construct a bridge on Wilhelm Road between Allen Road and Radnor Road | 2700000 | Scott Reeise | Contractor has completed the majority of the remaining bridge work. | Bridge is scheduled to open August 3.
5 | Orange Prairie Rt. 150 to Alta Ln. | Design and construct Orange Prairie Road from Rt. 150 to Rt. 91 | 15000000 | Nick Stoffer/Scott Reeise/Jeff Smith | ROW negotiations are continuing on North Project. Farnsworth has split the plans into two phases on the north end so a project to continue the road up to Pioneer Parkway extended can be bid. All but one ROW parcel has been acquired and this is proving to be difficult. The contractor has begun pouring pavement on the South project and making good progress. | The remaining portions of pavement will be poured in August. Punch list and project paperwork should be completed in September.
3, 4, 5 | Northmoor - Sheridan Intersection (Stage 1) | Construct the intersection of Northmoor and Sheridan with new lanes and traffic signals, and sidewalks. 70% of the construction to be paid with Federal STP-U funds and City and County to split the costs of the local share of construction and the ROW and engineering costs. | 3382000 | Scott Reeise | Council approved addendum #1 to the Hanson contract to close out the construction on May 22, 2012. | Working with contractor on agreement to final quantities. Project is complete and paperwork still is needed to be turned over to IDOT.
5 | Allen and Hickory Grove Intersection | Improve intersection in conjunction with the construction of a new Dunlap School. Construction anticipated in 2012. | Funded by Dunlap School District $1.3 M | Nick Stoffer | Construction started July 7, 2012. | Contractor should continue working on Roundabout and place curb and gutter in August.
3 | Pennsylvania Ave | Remove and replace the pavement on Pennsylvania Ave. from Berkeley Ave. to Glen Oak Ave. Includes ornamental lighting and a new storm sewer system. The intersection of Glen Oak and New York/Wayne St. will be configured as a round-a-bout. Armstrong Ave. will be closed at New York. | 5153000 | Scott Reeise | Pavement on Glen Oak was completed and the roundabout itself has been completed. The landscaping change order was approved on July 24. | Contractor should finish Stage I of the project and open the roundabout in mid to late August and then switch over to Stage II which will take Pennsylvania Avenue to California Ave.
2 | McClure and Loucks Intersection | Improve intersection of McLure and Loucks per Council direction. | 205000 | Scott Reeise | Council awarded the project on May 8, 2012. | This project is schedule to start in early August.
PROJECTS TO BID AND START CONSTRUCTION SOON
4, 5 | Northmoor - Sheridan to University (Stage 2) | Construct Northmoor with three lanes, curbs, and sidewalks/bike paths between Sheridan and University. This project is funded 70% Federal STP-U funds with the City and County splitting the remainder equally. | 2835000 | Scott Reeise | This project was let June 15 on an IDOT letting. IDOT has not awarded the project yet. | Once an award letter is received from IDOT a preconstruction meeting will be held and construction will begin by late August or early September.
1 | US 24/Washington Street | Conduct Phase 1 preliminary design for this route between I-474 and I-74. Complete Phase 2 design for section from Main to Maple. | 10730000 | Jeff Smith and Scott Reeise | Coordinated with IAWC for water main replacement and CAT for work around the CAT parking deck. The contractor started work. | Construction will be substantially complete by the end of August on all the roadwork in the Museum Block. The section of Washington Street between Liberty and Walnut should be advertised for bid in September with work starting on October.
PROJECTS UNDER DESIGN AND/OR ROW ACQUISITION
5 | Alta/Radnor Intersection | This project will construct the intersection of Radnor Rd and Alta Rd. A roundabout will be constructed. | 1400000 | Scott Reeise | The intersection design study and preliminary design report have been competed and approved by IDOT. Terra was hired for appraisals and ROW negotiations. ROW plats were completed and appraisals have been completed and ROW negotiation have begun. An extension to the DCEO grant agreement was requested. IDOT is withholding plan approval pending further discussions on jurisdictional transfers. | Utility coordination will continue. ROW negotiations will be continued in August.
1 | Warehouse District Tiger II | This grant will assist in building public infrastructure to support the redevelopment of the Warehouse District. | 13800000 | Jeff Smith | The grant agreement amendment with FHWA for construction funding was approved along with eh IDOT agreement. Final plans were submitted to IDOT on schedule. The Phase III Construction Engineering Services agreement with Terra Engineering was approved. ROW appraisals were completed. | Funds for the project will be Obligated by FHWA. Utility coordination and ROW negotiations will continue.
5 | Pioneer Parkway Extension- ROW Acquisition--Radnor to Harker | Agreement with consultant for ROW services and funding for ROW purchases. | 1450000 | Jane Gerdes | Agreement with consultant for ROW approved on June 26, 2012, subject to IDOT approval. A Federal grant will reimburse 80% of the cost. | Agreement under review by IDOT.
5 | Pioneer Parkway Extension - Design - Villa Lake to Harker | Agreement with consultant to design the first segment of Pioneer Parkway extension from Villa Lake Drive to Harker Drive, including the intersection at Allen Road. | 474414 | Jane Gerdes | Agreement with consultant approved on July 24, 2012, subject to IDOT approval. A Federal grant will reimburse 80% of the cost. | Agreement under review by IDOT.
| Private Property Drainage 2012-2014 | Administer the Private Property Drainage Assistance Program and Sanitary Sewer Backup Assistance Program | 200000 | Jane Gerdes | Consultant working with homeowners on drainage repairs. | Consultant working with homeowners on drainage repairs.
All | Drainage Improvements 2012-2014 | Repair failing drainage infrastructure | 400000 | Jane Gerdes | Project was advertised for bid. Construction contract was awarded on June 26, 2012. | Begin construction.
All | Sidewalk Participation 2012 | Repair sidewalks as requested by property owners. | 485000 | Stephen Letsky | Council approved contract award on May 22, 2012. Work is approximately 50% complete in late July. | Sidewalk reconstruction will continue until funding is used up. Projected finish is around mid September.
NEXT PROJECTS TO START DESIGN
3, 4 | Arterial Street Overlay 2012-2014 | Overlay projects will focus on University Street and Forest Hill and include accessibility features. | 12000000 | Stephen Letsky | Consultant working on Design of University Street, final plans expected in August. The Work Order for Forrest Hill will be issued in early August, pending IDOT BLR approval of MFT Application. | Design for University Street is ongoing. Design for Forrest Hill will begin in August, pending IDOT BLR approval of MFT Application.
2 | Arterial Street Reconstruction 2012-2014 | Reconstruction projects will focus on Sheridan, Nebraska, McLure, and Wisconsin | 2700000 | Stephen Letsky | Planning on strategy and sequencing underway. Sheridan Road will be worked on. Funding for the entire road does not exist, so the plan is to reconstruct McClure to Richmond (north of I-74 bridge). | Design for Sheridan to commence in August, pending IDOT BLR approval of MFT Agreement.
All | ADA Ramps 2012-2014 | Replace existing non-compliant Ramps with ADA-compliant Ramps. | 600000 | Stephen Letsky | Advertised on 7/25/12. | Letting to occur on August 15. Going to Council for Contract Award on August 28.
All | SINR 2012-2014 | Repair sidewalks that are hazardous as determined by PGM or through complaints | 720000 | Stephen Letsky | Letting held on 7/6/12. Going to Council on August 14 - needed EEO approval. | Going to Council for Contract Award approval on August 14. Work to commence by September 4th.
3 | Glen Oak sidewalks Phase V | Complete repairs to the remaining sidewalks in the Glen Oak Impact Zone | 150000 | Stephen Letsky | Contract Award approved by Council on 7/10/12. Horowitz Concrete is low bidder, currently working on Bond paperwork. | Bond paperwork due August 2nd. Preconstruction meeting scheduled for August 3. Work to commence August 6.
1 | Harrison Impact Zone 2012-2014 | Continue infrastructure improvements in the Harrison Impact Zone with focus on drainage, curbs, and sidewalks | 900000 | Stephen Letsky | First part of Harrison Impact Zone is being advertised on 7/25/12 for Folkers Avenue Reconstruction. Sidewalk quantities will be examined by 7/31/12 for separate bid contract. | Bid letting will occur on August 15 for first part of Harrison Impact Zone. Going to Council on August 28. Advertise sidewalk reconstruction in north area by mid August.
5 | Growth Cell Sidewalks/Bike paths 2012-2014 | Identify needs for completing sidewalks and bike paths in the growth cells, acquire necessary ROW and install paths and walks. | 425000 | Stephen Letsky | Council approved selection process on March 13, 2012 and master agreements for design and construction engineering on April 24. | Will work with Planning Department on project identification and strategy before beginning design.
1 | Elm-Reed Sewer Relocation | Complete the design and follow through with the special assessment process and construction | 25000 | Stephen Letsky | Work Order was executed on June 12. Preliminary meetings with GPSD and City held in June and July. | Consultant to begin design of sewer relocation and upgrades in August. IEPA 90-day review will be initiated in mid to late August.
3 | Stonegate Special Assessment | Complete the design and follow through with the special assessment process and construction | 125000 | Stephen Letsky | Consultant work order was issued in May, and design work began. Initial Board of Local Improvements meeting was held on 7/12/12, and Stonegate's design to be redone to accommodate drainage concerns. Going back to BLI for approval in July. | Consultant revisiting roadway design to accommodate drainage concerns. Final Plans expected to be approved by 7/27/12. Going back to BLI for final approval prior to sending Assessment Roll to Circuit Court. Construction is expected to begin in early 2013 rather than late 2012, pending Circuit Court approval.
1 | Leonard Marshall Plaza | Replace deteriorated granite slabs | 125000 | Scott Reeise | Visited site and reviewed scope of work. Found that repairs could be done for significantly less cost. Quote was received form one contractor specializing in this type of work. | Will request Council approve a construction contract.
PROJECTS IN PLANNING PHASE and ONGOING PROGRAMS
N/A | Combined Sewer Overflows | Complete the Long Term Control Plan for the Combined Sewer area | TBD | Jane Gerdes | Provided testimony related to Integrated Planning Approach. | Continue negotiations.
5 | Pioneer Parkway | Complete an environmental and preliminary design study for Pioneer Parkway between Knoxville and Trigger Rd | 72400000 | Jane Gerdes | Preliminary Design Report was approved from Trigger to Woodsage and from Radnor to Allen. After discussion with IDOT regarding the RR bridge approval, an amendment to the consultant contract was approved on July 24, 2012. | Begin coordination with the RR about the proposed bridge design.
All | GPSD/Wildcat Sewers | Sanitary Sewer laterals serving multiple properties before connecting to the public sanitary sewer system | 28000 | Jane Gerdes | Continue working with GPSD on problems as they occur. Will address Wildcat sewers as problems occur. | Continue working with GPSD on problems as they occur. Will address Wildcat sewers as problems occur.
All | Stormwater Management-Clean Water Act 2012-2014 | Comply with Clean Water Act and 6 components. | 150000 | Jane Gerdes | Work began. Had initial meetings for Rain Garden grant program through Illinois American Water Company. Developed GIS mapping plan. | Begin annual dry-weather screening and mapping of storm sewers.
All | GIS Sidewalk Database | This project will provide asset management information in a GIS format for sidewalks and accessibility features (ramps). | 175000 | Stephen Letsky | Consultant given executed Work Order on July 9. | Consultant is in the field working from previous Pilot area and expanding the zone. Inventory in 2012 will complete approximately 1/4 of total Peoria area.
1 | Southtown Improvements | Various street, sidewalk, lighting, and bridge work | 230000 | Scott Reeise | Council approved an engineering agreement with Infrastructure Inc on July 24 | Design work will begin.
PROJECTS ON HOLD and OTHER PENDING PROJECTS
2 | Avalon Place Lighting | Special Assessment project to install ornamental lighting on Avalon Place from Forrest Hill to Hudson | 65000 | TBD | Bid letting was held August 16, 2011. Only one bidder was over 20% engineer's estimate. Board of Local Improvements rejected bids. Assessment roll was pulled from court so project would need to start over. Neighborhood was re-surveying petitioners to gage their current level of interest. | Board of Local Improvements meeting, held on 7/12/12, discussed importance of keeping these Special Assessment projects alive. Council direction will be sought.
2, 3 | Lighting Projects | Special Assessment project to install ornamental lighting on | 190000 | TBD | Neighborhood was re-surveying petitioners to gage their current level of interest. | Board of Local Improvements meeting, held on 7/12/12, discussed importance of keeping these Special Assessment projects alive. Council direction will be sought.