## Capital Projects Report
|  |  | 2012-04-30 |  | Prepared By Public Works Department - Engineering Division
Primary Council District | Project | Scope | Budget | Contact | Previous Month Activities | May Planned Activities
PROJECTS UNDER CONSTRUCTION
3 | 2011 ADA Ramp Project | Install ADA compliant curb ramps to improve the City's sidewalk system and accessibility. | $78.447.21 | Scott Reeise | Several ramps completed on McClure | Construction to be completed in May 2012.
5 | Radnor, Pioneer Parkway, and other RR Xings | Reconstruct Radnor RR Xing per ICC order | 157800 | Scott Reeise | Radnor Road and the Pioneer Parkway crossings were completed in December 2011. Work was done at Gilles, Knoxville, Vine, Bishop,and PJStar | Project Complete
4 | Ridge Road Sidewalks and Lighting | Special Assessment Project to install lighting and sidewalks on Ridge Road from Sheridan to Isabell Ave | 825000 | Scott Reeise | Contractor finished all road and sidewalk work and street lighting work. Landscaping is also completed. | Final pay estimate and punch will be compiled.
2 | Sidewalks In Need of Repair 38 - 2011 | To maintain a safe walking surface for the citizens of Peoria. | 250000 | Stephen Letsky | Ordaz is contractor. Construction started in second week of August. Work resumed in April on Gift. | Construction will continue on Gift and W Virginia and should be complete by May 31.
2 | Main Street | Restripe Main Street between Glendale and Sheridan per HSIP grant. Additionally, to restripe between University and Sheridan using City funds. | HSIP grant $43,642 ($4849 local match). No budget for additional work | Nick Stoffer | Road diet paint striping installed by City staff. | Ordering and installation of warning signs to begin once IDOT approves plans and estimates.
3, 4, 5 | Northmoor - Knoxville to Sheridan (Stage 3) | Construct Northmoor with three lanes, curbs, and sidewalks/bike paths between Knoxville and Sheridan. This is an ARRA Stimulus Project | 2391543 | Scott Reeise | Punch list items were completed in September. Council approved a contract with Hanson Professional Services, Inc. to final out the federal paperwork. | Working with contractor on agreement to final quantities. Project is complete and paperwork still is needed to be turned over to IDOT.
5 | Wilhelm Bridge | Construct a bridge on Wilhelm Road between Allen Road and Radnor Road | 2700000 | Scott Reeise | Contractor has completed both piers and the abutment on the west end of the project. Work resumed on south abutment and test pile was installed | Piling will be completed and east abutment installed. Bridge should open in July.
5 | Orange Prairie Rt. 150 to Alta Ln. | Design and construct Orange Prairie Road from Rt. 150 to Rt. 91 | 15000000 | Nick Stoffer/Scott Reeise/Jeff Smith | The pavement widening from 700' north of War Memorial Drive north to American Prairie Drive was completed by the end of November. Design engineering and property acquisition for the northern phase continued. Work resumed on storm sewer on south end. | ROW negotiations are continuing on North Project for a spring 2012 letting. Farnsworth will split the plans into two phases on the north end so a project to continue the road up to Pioneer Parkway can be bid by mid-summer. In May contractor will complete the storm sewer and begin excavation for the pavement.
Varies | 2011 Drainage Repair Contract | Various | 400000 | Scott Reeise | Final closeout was done. | Closed out.
3, 4, 5 | Northmoor - Sheridan Intersection (Stage 1) | Construct the intersection of Northmoor and Sheridan with new lanes and traffic signals, and sidewalks. 70% of the construction to be paid with Federal STP-U funds and City and County to split the costs of the local share of construction and the ROW and engineering costs. | 3382000 | Scott Reeise | Council approved a contract with Hanson Professional Services, Inc. to final out the federal paperwork. The contractor has completed all major work on the project. Work to close out project documentation continued. | Project documentation will continue until complete and approved by IDOT.
5 | Allen and Hickory Grove Intersection | Improve intersection in conjunction with the construction of a new Dunlap School. Construction anticipated in 2012. | Funded by Dunlap School District $1.3 M | Nick Stoffer | Dunlap awarded the bid in April | Neighborhood project meeting is scheduled for June 7. Work will begin about July 1 with construction complete in late October.
PROJECTS TO BID AND START CONSTRUCTION SOON
3 | Pennsylvania Ave | Remove and replace the pavement on Pennsylvania Ave. from Berkeley Ave. to Glen Oak Ave. Includes ornamental lighting and a new storm sewer system. The intersection of Glen Oak and New York/Wayne St. will be configured as a round-a-bout. Armstrong Ave. will be closed at New York. | 5153000 | Scott Reeise | Construction contract for first phase was approved by Council and a preconstruction meeting was help with contractor and utilities. | Neighborhood meeting will be held . Construction on Wayne, Armstrong, Glen Oak, and Pennsylvania beginning Peoria's first roundabout.
2 | McClure and Loucks Intersection | Improve intersection of McLure and Loucks per Council direction. | 205000 | Scott Reeise | Design was complete and project was bid. | Council award is scheduled for May 8. Work should begin in late May or early June.
4, 5 | Northmoor - Sheridan to University (Stage 2) | Construct Northmoor with three lanes, curbs, and sidewalks/bike paths between Sheridan and University. This project is funded 70% Federal STP-U funds with the City and County splitting the remainder equally. | 2835000 | Scott Reeise | Plans were completed and approved for bid by IDOT. ROW acquisition was complete and sent to IDOT for certification. | Project is scheduled for a June 15 IDOT letting. Work should begin by early August.
PROJECTS UNDER DESIGN AND/OR ROW ACQUISITION
5 | Alta/Radnor Intersection | This project will construct the intersection of Radnor Rd and Alta Rd. A roundabout will be constructed. | 1400000 | Scott Reeise | The intersection design study and preliminary design report have been competed and approved by IDOT. Terra was hired for appraisals and ROW negotiations. ROW plats were completed and appraisals have been ordered. | Final plans will be done and submitted to IDOT. Utility coordination will continue. ROW negotiations will begin. The target time for bidding is July depending on ROW acquisition.
1 | US 24/Washington Street | Conduct Phase 1 preliminary design for this route between I-474 and I-74. Complete Phase 2 design for section from Main to Maple. | 10730000 | Jeff Smith | Work continued corresponding to IDOT comments on the Preliminary Design report. IDOT is still working on completing the PSI. Draft JT agreement was received but we are awaiting IDOT's assessment and commitment to value before sending to Council. Held WAG meeting. Working with PRM and CVC projects to coordinate work between Main and Liberty. Also coordinating with IAWC for water main replacement and CAT for work around the CAT parking deck. Plans for work between Liberty and Main were sent to IDOT for approval. | Bidding will be undertaken for first project between Main and Liberty. Council award will be in June. Plans will continue for section from Liberty to Walnut with a mid summer bid anticipated. The section from Walnut to Maple will be scheduled for a late fall bidding to coincide with the TIGER letting in November. Material bids are being solicited for traffic signals to speed up the construction process.
1 | Warehouse District Tiger II | This grant will assist in building public infrastructure to support the redevelopment of the Warehouse District. | 13800000 | Jeff Smith | Preliminary Design Report was completed on schedule in Dec 2011. | Council policy session is scheduled for February 4, 2012. Final design continues with completion deadline of June 30. Council policy Session was held on Feb 4.
All | Sidewalk Participation 2012 | Repair sidewalks as requested by property owners. | 485000 | Stephen Letsky | CIP Approved by Council. Consultant Selection Process was undertaken during December and January. Council approved selection process on March 13, 2012 and a consultant contract with Herman and Assoc in April. Bids were received for the construction. | Construction contract award is scheduled for May 8 Council award. Consultant work order will be issued to initiate the 2012 program.
NEXT PROJECTS TO START DESIGN
3, 4 | Arterial Street Overlay 2012-2014 | Overlay projects will focus on University Street and Forest Hill and include accessibility features. | 12000000 | Stephen Letsky | CIP Approved by Council. Consultant Selection Process was undertaken during December and January. Council approved selection process on March 13, 2012 and master agreements for design and construction engineering on April 24. | Consultant work orders will be issued and design work will begin.
2 | Arterial Street Reconstruction 2012-2014 | Reconstruction projects will focus on Sheridan, Nebraska, McLure, and Wisconsin | 2700000 | Stephen Letsky | CIP Approved by Council. Consultant Selection Process was undertaken during December and January. Council approved selection process on March 13, 2012 | Consultant contracts will be negotiated and brought to Council in subsequent months
All | Drainage Improvements 2012-2014 | Repair failing drainage infrastructure including retaining wall at Humbolt and Prospect | 1200000 | Jane Gerdes | CIP Approved by Council. Consultant Selection Process was undertaken during December and January. Council approved selection process on March 13, 2012 and master agreements for design and construction engineering on April 24. | Consultant work orders will be issued and design work will begin.
All | Private Property Drainage 2012-2014 | Administer the Private Property Drainage Assistance Program and Sanitary Sewer Backup Assistance Program | 600000 | Jane Gerdes | CIP Approved by Council. Consultant Selection Process was undertaken during December and January. Council approved selection process on March 13, 2012 and master agreements for design and construction engineering on April 24. | Consultant work orders will be issued and design work will begin.
All | ADA Ramps 2012-2014 | Complete inventory and | 600000 | Stephen Letsky | CIP Approved by Council. Consultant Selection Process was undertaken during December and January. Council approved selection process on March 13, 2012 and master agreements for design and construction engineering on April 24. | Consultant work orders will be issued and design work will begin.
All | SINR 2012-2014 | Repair sidewalks that are hazardous as determined by PGM or through complaints | 720000 | Stephen Letsky | CIP Approved by Council. Consultant Selection Process was undertaken during December and January. Council approved selection process on March 13, 2012 and master agreements for design and construction engineering on April 24. | Consultant work orders will be issued and design work will begin.
3 | Glen Oak sidewalks Phase V | Complete repairs to the remaining sidewalks in the Glen Oak Impact Zone | 150000 | Stephen Letsky | CIP Approved by Council. Consultant Selection Process was undertaken during December and January. Council approved selection process on March 13, 2012 and master agreements for design and construction engineering on April 24. | Consultant work orders will be issued and design work will begin.
1 | Harrison Impact Zone 2012-2014 | Continue infrastructure improvements in the Harrison Impact Zone with focus on drainage, curbs, and sidewalks | 900000 | Stephen Letsky | CIP Approved by Council. Consultant Selection Process was undertaken during December and January. Council approved selection process on March 13, 2012 and master agreements for design and construction engineering on April 24. | Consultant work orders will be issued and design work will begin.
5 | Growth Cell Sidewalks/Bike paths 2012-2014 | Identify needs for completing sidewalks and bike paths in the growth cells, acquire necessary ROW and install paths and walks. | 425000 | Stephen Letsky | CIP Approved by Council. Consultant Selection Process was undertaken during December and January. Council approved selection process on March 13, 2012 and master agreements for design and construction engineering on April 24. | Consultant work orders will be issued and design work will begin.
1 | Leonard Marshall Plaza | Replace deteriorated granite slabs | 125000 | Scott Reeise | Visited site and reviewed scope of work. Found that repairs could be done for significantly less cost. | Will dicuss alternate methods with contractors to find ways to complete repairs at the lowest cost possible.
3 | Stonegate Special Assessment | Complete the design and follow through with the special assessment process and construction | 850000 | Stephen Letsky | CIP Approved by Council. Consultant Selection Process was undertaken during December and January. Council approved selection process on March 13, 2012 and master agreements for design and construction engineering on April 24. | Consultant work orders will be issued and design work will begin.
PROJECTS IN PLANNING PHASE and ONGOING PROGRAMS
N/A | Combined Sewer Overflows | Complete the Long Term Control Plan for the Combined Sewer area | TBD | Jane Gerdes | Met with USEPA on November 1 and 2. Continued negotiations. | Continue negotiations.
5 | Pioneer Parkway | Complete an environmental and preliminary design study for Pioneer Parkway between Knoxville and Trigger Rd | TBD | Jane Gerdes | Received partial approval on the Preliminary Design Report. | Look for a way to fund an effort to approach the ICC to reduce the potential cost for the Railroad crossing. Should hear back on the TIGET 2012 grant application.
All | GPSD/Wildcat Sewers | Sanitary Sewer laterals serving multiple properties before connecting to the public sanitary sewer system | 28000 | Jane Gerdes | Worked with the GPSD on problems near Glen Oak School. | Continue working with GPSD on problems as they occur. Will address Wildcat sewers as problems occur.
All | Stormwater Management-Clean Water Act 2012-2014 | Comply with Clean Water Act and 6 components. | 450000 | Jane Gerdes | CIP Approved by Council. Consultant Selection Process was undertaken during December and January. Council approved selection process on March 13, 2012 and master agreements for design and construction engineering on April 24. | Consultant contracts will be negotiated and brought to Council in subsequent months
PROJECTS ON HOLD
2 | Avalon Place Lighting | Special Assessment project to install ornamental lighting on Avalon Place from Forrest Hill to Hudson | 65000 | Stephen Letsky | Bid letting was held August 16, 2011. Only one bidder was over 20% engineer's estimate. Board of Local Improvements rejected bids. Assessment roll was pulled from court so project would need to start over. Neighborhood was re-surveying petitioners to gage their current level of interest. | Board of Local Improvements meeting will be scheduled for a decision on how to proceed.
2, 3 | Lighting Projects | Special Assessment project to install ornamental lighting on | 190000 | Stephen Letsky | Neighborhood was re-surveying petitioners to gage their current level of interest. | Board of Local Improvements meeting will be scheduled for a decision on how to proceed.