## Capital Projects Report
|  |  | 2012-03-28 |  | Prepared By Public Works Department - Engineering Division
Primary Council District | Project | Scope | Budget | Contact | Previous Month Activities | Next Month Planned Activities
PROJECTS UNDER CONSTRUCTION
3 | 2011 ADA Ramp Project | Install ADA compliant curb ramps to improve the City's sidewalk system and accessibility. | $78.447.21 | Scott Reeise | Several ramps complete. | Construction will recommence in April and will be completed in 2012.
5 | Radnor, Pioneer Parkway, and other RR Xings | Reconstruct Radnor RR Xing per ICC order | 157750 | Scott Reeise | The majority of the RR crossing work at both the Radnor Road and the Pioneer Parkway crossings was completed in December 2011 | The remaining work to remove crossings will most likely take place in April or May.
4 | Ridge Road Sidewalks and Lighting | Special Assessment Project to install lighting and sidewalks on Ridge Road from Sheridan to Isabell Ave | 825000 | Scott Reeise | Contractor finished all road and sidewalk work and street lighting work. Landscaping is also completed. | Final pay estimate and punch list will be compiled.
2 | Sidewalks In Need of Repair 38 - 2011 | To maintain a safe walking surface for the citizens of Peoria. | 250000 | Stephen Letsky | Ordaz is contractor. Construction started in second week of August. Construction wrapped up for 2011. 50% complete. | Construction to be completed Spring 2012.
2 | Main Street | Restripe Main Street between Glendale and Sheridan per HSIP grant. Additionally, to restripe between University and Sheridan using City funds. | HSIP grant $43,642 ($4849 local match). No budget for additional work | Nick Stoffer | Road diet paint striping installed by City staff. | Ordering and installation of warning signs to begin once IDOT approves plans and estimates.
3, 4, 5 | Northmoor - Knoxville to Sheridan (Stage 3) | Construct Northmoor with three lanes, curbs, and sidewalks/bike paths between Knoxville and Sheridan. This is an ARRA Stimulus Project | 2391543 | Scott Reeise | Punch list items were completed in September. Council approved a contract with Hanson Professional Services, Inc. to final out the federal paperwork. | Working with contractor on agreement to final quantities. Project is complete and documentation still is needed to be turned over to IDOT.
5 | Wilhelm Bridge | Construct a bridge on Wilhelm Road between Allen Road and Radnor Road | 2700000 | Scott Reeise | Contractor has completed both piers and the abutment on the west end of the project. Council approved a contract with Maurer-Stutz to take over construction inspection duties. Project was shut down over winter. | Project will restart in early April. Weather depending it is anticipated that this work will be completed in July 2012.
5 | Orange Prairie Rt. 150 to Alta Ln. | Design and construct Orange Prairie Road from Rt. 150 to Rt. 91 | 15000000 | Nick Stoffer/Scott Reeise/Jeff Smith | The pavement widening from 700' north of War Memorial Drive north to American Prairie Drive was completed by the end of November. Design engineering and property acquisition for the northern phase continued. | Farnsworth Engineering was hired to complete the construction contract on the South Project. Work was restarted in later March. Final design continues on the North Project and ROW appraisals and negotiations are taking place on the North Project. A project on the North can be advertised when ROW is acquired to Pioneer Parkway extended.
Varies | 2011 Drainage Repair Contract | Various | 400000 | Scott Reeise | Complete
3, 4, 6 | Northmoor - Sheridan Intersection (Stage 1) | Construct the intersection of Northmoor and Sheridan with new lanes and traffic signals, and sidewalks. 70% of the construction to be paid with Federal STP-U funds and City and County to split the costs of the local share of construction and the ROW and engineering costs. | 3382000 | Scott Reeise | Council approved a contract with Hanson Professional Services, Inc. to final out the federal documentation. The contractor has completed all major work on the project. | Hanson will develop a punch list for the contractor to complete and final the job in second quarter 2012.
5 | Allen and Hickory Grove Intersection | Improve intersection in conjunction with the construction of a new Dunlap School. Construction anticipated in 2012. | Funded by Dunlap School District $1.3 M | Scott Reeise | Bid opening was on March 7. An amendment to the agreement with Dunlap School Dist will be on the March 27 Council agenda. | Construction is expected to begin around July 1 and the intersection is expected to be closed for 17 weeks with all work complete by the end of 2012.
PROJECTS TO BID AND START CONSTRUCTION SOON
3 | Pennsylvania Ave | Remove and replace the pavement on Pennsylvania Ave. from Berkeley Ave. to Glen Oak Ave. Includes ornamental lighting and a new storm sewer system. The intersection of Glen Oak and New York/Wayne St. will be configured as a round-a-bout. Armstrong Ave. will be closed at New York. | 750000 | Scott Reeise | ROW agreement with OSF was approved Terra Engineering has begun to negotiate ROW for Phase 2. The bid opening for the first project, which includes the roundabout, was held on March 22 and Stark Excavating is the apparent low bidder | The bid award will be scheduled for the April 10 Council meeting and work is expected to begin about May 1. A consulting engineering services agreement will also be on an April Council agenda.
2 | McClure and Loucks Intersection | Improve intersection of McLure and Loucks per Council direction. | 250000 | Scott Reeise | Farnsworth Group has completed the design. | Bid opening is scheduled for April 12 and award by Council on April 24.
4, 5 | Northmoor - Sheridan to University (Stage 2) | Construct Northmoor with three lanes, curbs, and sidewalks/bike paths between Sheridan and University. This project is funded 70% Federal STP-U funds with the City and County splitting the remainder equally. | 2835000 | Scott Reeise | Terra Engineering was contracted with to perform ROW negotiations on the project. No response has been received from AmerenCilco at the possibility of moving overhead lines underground. Appraisals have been completed and ROW negotiations are underway. | Hanson Professional Services will complete the plans and submit them to IDOT for approval. Terra Engineering Services will continue with negotiating the ROW. This project is scheduled to be on the June IDOT letting to start construction in 2012.
PROJECTS UNDER DESIGN AND/OR ROW ACQUISITION
5 | Alta/Radnor Intersection | This project will construct the intersection of Radnor Rd and Alta Rd. A roundabout will be constructed. | 1400000 | Scott Reeise | The intersection design study and preliminary design report have been competed and approved by IDOT. Final design of a roundabout is underway. Staff is working with the consultant to minimize the ROW requirements. Terra was hired for appraisals and ROW negotiations. ROW plats will be finalized and appraisals can then be ordered. | Final plans will be done and submitted to IDOT. Utility coordination will be initiated. Final ROW plates will be completed and appraisals will be ordered. ROW negotiations will begin after the appraisals are returned. Bidding can be done after ROW is acquired and after the final plans are approved by IDOT.
1 | US 24/Washington Street | Conduct Phase 1 preliminary design for this route between I-474 and I-74. Complete Phase 2 desing for section from Harrison to Maple and Harrison to Main. | 10730000 | Jeff Smith | The Preliminary Design report was submitted to IDOT. IDOT will not complete the PSI until May. Staff has been in contact regarding the JT agreement. Coordination has been discussed with the CVC and Museum developers. The first project is planned to take place between Liberty and Main. Final design is being done on the next phase of construction which would be between Liberty and Walnut and include the Harrison roundabout. | IDOT will comment on the Preliminary Design Report. Negotiations for Cohen ROW parcels at Harrison will be done by the Legal Dept. Final design will continue on section from Harrison to Maple and design will be completed on the section from Liberty to Main. This first stage will bid in May providing IDOT completes the PSI and approves the plans.
1 | Warehouse District Tiger II | This grant will assist in building public infrastructure to support the redevelopment of the Warehouse District. | 13800000 | Jeff Smith | The preliminary project report, PESA, geotechnical report, and preliminary intersection IDS's were all completed on schedule and approved in December. Final design work is underway. A Federal project review was conducted and staff has been working with IDOT and FHWA to address changes to the Grant Agreement. | Final design continues with completion deadline of June 30. Staff will continue to work with IDOT and FHWA on an amendment to the Grant Agreement. The project is scheduled for the November 9,2012 IDOT letting.
All | Sidewalk Participation 2012 | Repair sidewalks as requested by property owners. | 485000 | Stephen Letsky | CIP Approved by Council. Consultant Selection Process was undertaken during December and January. Council approved selection process on March 13, 2012 | Staff will get the construction contract out to bid with Council award in April. Consultant contracts will be negotiated and brought to Council in April.
NEXT PROJECTS TO START DESIGN
3, 4 | Arterial Street Overlay 2012-2014 | Overlay projects will focus on University Street and Forest Hill and include accessibility features. | 12000000 | Stephen Letsky | CIP Approved by Council. Consultant Selection Process was undertaken during December and January. Council approved selection process on March 13, 2012 | Consultant contracts will be negotiated and brought to Council in April
2 | Arterial Street Reconstruction 2012-2014 | Reconstruction projects will focus on Sheridan, Nebraska, McLure, and Wisconsin | 2700000 | Stephen Letsky | CIP Approved by Council. Consultant Selection Process was undertaken during December and January. Council approved selection process on March 13, 2012 | Consultant contracts will be negotiated and brought to Council in April
All | Drainage Improvements 2012-2014 | Repair failing drainage infrastructure including retaining wall at Humbolt and Prospect | 1200000 | Jane Gerdes | CIP Approved by Council. Consultant Selection Process was undertaken during December and January. Council approved selection process on March 13, 2012 | Consultant contracts will be negotiated and brought to Council in April
All | Private Property Drainage 2012-2014 | Administer the Private Property Drainage Assistance Program and Sanitary Sewer Backup Assistance Program | 600000 | Jane Gerdes | CIP Approved by Council. Consultant Selection Process was undertaken during December and January. Council approved selection process on March 13, 2012 | Consultant contracts will be negotiated and brought to Council in April
All | ADA Ramps 2012-2014 | Complete inventory and construct ramps | 600000 | Stephen Letsky | CIP Approved by Council. Consultant Selection Process was undertaken during December and January. Council approved selection process on March 13, 2012 | Consultant contracts will be negotiated and brought to Council in April
All | SINR 2012-2014 | Repair sidewalks that are hazardous as determined by PGM or through complaints | 720000 | Stephen Letsky | CIP Approved by Council. Consultant Selection Process was undertaken during December and January. Council approved selection process on March 13, 2012 | Consultant contracts will be negotiated and brought to Council in April
3 | Glen Oak sidewalks Phase V | Complete repairs to the remaining sidewalks in the Glen Oak Impact Zone | 150000 | Stephen Letsky | CIP Approved by Council. Consultant Selection Process was undertaken during December and January. Council approved selection process on March 13, 2012 | Consultant contracts will be negotiated and brought to Council in April
1 | Harrison Impact Zone 2012-2014 | Continue infrastructure improvements in the Harrison Impact Zone with focus on drainage, curbs, and sidewalks | 900000 | Stephen Letsky | CIP Approved by Council. Consultant Selection Process was undertaken during December and January. Council approved selection process on March 13, 2012 | Consultant contracts will be negotiated and brought to Council in April
5 | Growth Cell Sidewalks/Bike paths 2012-2014 | Identify needs for completing sidewalks and bike paths in the growth cells, acquire necessary ROW and install paths and walks. | 425000 | Stephen Letsky | CIP Approved by Council. Consultant Selection Process was undertaken during December and January. Council approved selection process on March 13, 2012 | Consultant contracts will be negotiated and brought to Council in April
1 | Leonard Marshall Plaza | Replace deteriorated granite slabs | 125000 | Stephen Letsky | CIP Approved by Council. Consultant Selection Process was undertaken during December and January. Council approved selection process on March 13, 2012 | Consultant contracts will be negotiated and brought to Council in April
1 | Elm - Reed Sewer Relocation | Relocate the sanitary sewer running through City owned land. This will make the lot more developable | 301200 | Stephen Letsky | Select a consulting engineer | Consultant contracts will be negotiated and brought to Council in April
3 | Stonegate Special Assessment | Complete the design and follow through with the special assessment process and construction | 850000 | Stephen Letsky | CIP Approved by Council. Consultant Selection Process was undertaken during December and January. Council approved selection process on March 13, 2012 | Consultant contracts will be negotiated and brought to Council in April
PROJECTS IN PLANNING PHASE and ONGOING PROGRAMS
N/A | Combined Sewer Overflows | Complete the Long Term Control Plan for the Combined Sewer area | TBD | Jane Gerdes | Met with USEPA on March 22. Continued negotiations. | Continue negotiations.
5 | Pioneer Parkway | Complete an environmental and preliminary design study for Pioneer Parkway between Knoxville and Trigger Rd | TBD | Jane Gerdes | Received and responded to IDOT comments on the final design report. Prepared and submitted a TIGER 2012 application. | Anticipate IDOT design approval. Hopefully will hear back regarding the TIGER 2012 application.
All | GPSD/Wildcat Sewers | Sanitary Sewer laterals serving multiple properties before connecting to the public sanitary sewer system | 28000 | Jane Gerdes | Worked with the GPSD on problems near Glen Oak School. | Continue working with GPSD on problems as they occur. Will address Wildcat sewers as problems occur.
All | Stormwater Management-Clean Water Act 2012-2014 | Comply with Clean Water Act and 6 components. | 450000 | Jane Gerdes | CIP Approved by Council. Consultant Selection Process was undertaken during December and January. Council approved selection process on March 13, 2012 | Consultant contracts will be negotiated and brought to Council in April
PROJECTS ON HOLD
2 | Avalon Place Lighting | Special Assessment project to install ornamental lighting on Avalon Place from Forrest Hill to Hudson | 65000 | Stephen Letsky | Bid letting was held August 16, 2011. Only one bidder was over 20% engineer's estimate. Board of Local Improvements rejected bids. Assessment roll was pulled from court so project would need to start over. Re-surveying petitioners to gage their current level of interest. | Survey results will be complield and presented to the Board of Local Improvements for a decision on how to proceed.
2 | Lighting Projects | Special Assessment project to install ornamental lighting on Elizabeth, Twelve Oaks and Flora | 190000 | Stephen Letsky | Re-surveying petitioners to gage their current level of interest. | Survey results will be complield and presented tot eh Board of Local Improvements for a decision on how to proceed.