## Capital Projects Report
| CAPITAL PROJECTS REPORT |  | 2011-09-01 |  | Prepared By Public Works Department - Engineering Division
Primary Council District | Project | Scope | Budget | Contact | Previous Month Activities | Next Month's Planned Activities
4 | Hollyhedges/Deveraux Drainage | Widen the channel of a stream and stabilize the streambank | 1590335 | Scott Reeise | Received the Letter of Map Revisions (LOMR) from consultant | Submit LOMR information to FEMA.
N/A | Combined Sewer Overflows | Complete the Long Term Control Plan for the Combined Sewer area | TBD | Jane Gerdes | Continued negotiations. | Meeting scheduled with USEPA on September 8, 2011 to review plan to date.
5 | Pioneer Parkway | Compete an environmental and preliminary design study for Pioneer Parkway between Knoxville and Trigger Rd | TBD | Jane Gerdes | Submit final additional information. | IDOT review. Meet with IDOT concerning possible federal rescission of earmark funding
5 | Radnor Road RR Xing | Reconstruct Radnor RR Xing per ICC order | 85000 | Scott Reeise | Request for Proposals to design and build the crossings at Pioneer Parkway and Radnor Road are due August 30, 2011. | RFP recommendation will go to City Council for approval September 13, 2011.
2 | Avalon Place Lighting | Special Assessment project to install ornamental lighting on Avalon Place from Forrest Hill to Hudson | Special Assessment Program | Mike Taylor | Bid letting was held August 16, 2011. Only one bidder was over 20% engineer's estimate. Board of Local Improvemetns rejected bids. | To be re-bid during September.
4 | Easton Place Sidewalk/Road | A Special Assessment project to construct new curbs on both sides and overlay the street and install new sidewalk on the west side. | Special Assessment Program | Scott Reeise | Construction 95% complete. | Contractor will work on punch list items and close project out in September.
All | GPSD/Wildcat Sewers | Sanitary Sewer laterals serving multiple properties before connecting to the public sanitary sewer system | 28000 | Mike Taylor | Worked with the GPSD on problems near Glen Oak School. | Continue working with GPSD on problems as they occur.
3 | Pennsylvania Ave | Remove and replace the pavement on Pennsylvania Ave. from Berkeley Ave. to Glen Oak Ave. Includes ornamental lighting and a new storm sewer system. The intersection of Glen Oak and New York/Wayne St. will be configured as a round-a-bout. Armstrong Ave. will be closed at New York. | 750000 | Scott Reeise | All ROW, except for OSF, has been approved and settled. | Continue working with OSF for final part of ROW. Complete final review, have IDOT approval, and have a bid letting in early 2012. Construction scheduled to begin in early 2012.
4 | Ridge Road Sidewalks and Lighting | Special Assessment Project to install lighting and sidewalks on Ridge Road from Sheridan to Isabell Ave | 825000 | Mike Taylor | Bid letting was held August 16, 2011. ICCI was apparent low bidder and Board of Local Improvemtns awarded the contract to them. | Construction set to begin in September and will carry over into 2012.
3 | Glen Oak Sidewalks Phase III | Replace deteriorated sidewalks to improve walking routes within the Glen Oak Impact Zone. | 200000 | Nick Stoffer | Contract completed.
3 | Glen Oak Sidewalks Phase IV (Durbin Grant) | Replace deteriorated sidewalks to improve walking routes within the Glen Oak Impact Zone. | 120000 | Nick Stoffer | Contract completed.
5 | Safer Neighborhood Sidewalks - Keller | Install new sidewalks within 3 blocks of school property to provide safe routes to school for students. | 175000 | Nick Stoffer | Horowitz is the contractor. Construction on Mt. Hawley next to Kellar School and will be complete. | Construction to continue through September.
1, 3 | Safer Neighborhood Sidewalks - Trewyn/Washington | Install new sidewalks within 3 blocks of school property to provide safe routes to school for students. | 200000 | Nick Stoffer | Combined with other project. Two drywells were installed at Trewyn to help with sidewalk flooding. | Washington project to be combined with the Kellar project as the Safer Neighborhood Sidewalk Program. Trewyn project to be removed as a stand alone CIP request for 2012, due to project complexity. Minor drainage improvements are being planned in conjunction with Unit 150 schools.
1 | Safer Neighborhood Sidewalks - Harrison | Install new sidewalks within 3 blocks of school property to provide safe routes to school for students. | 200000 | Scott Reeise | Council award contract on June 14, 2011 to Lorusso Cement Contractors. Construction started mid July. Construction approximately 80% complete. | Contractor should complete the work in early September.
All | Sidewalk Participation 2011 | Upgrade sidewalks within the City to create safe and attractive walking routes. | 385000 | Nick Stoffer | Construction began in April with C&G Concrete as the contractor. All project funds encumbered as of the end of June. Participation fund received added to the budget in late July and immediately encumbered with received applications. | Construction to continue to completion of encumbered funds.
All | Bridge Structure Repairs |  | 30000 | Nick Stoffer | None. | Hire testing company to take concrete core samples.
2 | Bridge Inspections | Inspect the Sheridan Rd and Nebraska Ave bridges in preparation of their replacement | 70000 | Nick Stoffer | None. | Request for proposals developed for inspection contracts in September.
2 | Sidewalks In Need of Repair 38 - 2011 | To maintain a safe walking surface for the citizens of Peoria. | 250000 | Nick Stoffer | Bid opening held June 26, 2011. Ordaz low bidder. Construction started in second week of August. 8% complete. | Construction to continue into November.
2 | Main Street | Restripe Main Street between Glendale and Sheridan per HSIP grant. Additionally, to restripe between University and Sheridan using City funds. | HSIP grant $43,642 ($4849 local match). No budget for additional work | Nick Stoffer | Paint striping installed by City staff. Additional paint striping ongoing. | Ordering and installation of warning signs to begin once IDOT approves plans and estimates.
5 | Orange Prairie Rt. 150 to Alta Ln. | Design and construct Orange Prairie Road from Rt. 150 to Rt. 91 | 15000000 | Nick Stoffer | Bid opened on August 11, R.A. Cullinan low bidder. Construction will begin in September after all contractual documents are processed. | Construction will commence in September and carry into mid 2012. Construction in 2011 will focus on widening the pavement from 700' north of War Memorial Drive north to American Prairie Drive. Engineering and property acquisition for the northern phase to continue.
1 | Downtown Arterial Streets | Overlay downtown streets and address pedestrian safety concerns | 550000 | Scott Reeise | No work has been started on this project to date. | Construction funds delayed until 2012. Coordination with Washington St design work will be required.
3, 4, 5 | Northmoor - Knoxville to Sheridan (Stage 3) | Construct Northmoor with three lanes, curbs, and sidewalks/bike paths between Knoxville and Sheridan. This is an ARRA Stimulus Project | 2391543 | Scott Reeise | Contractor will work on punch list items and project will begin close out process with IDOT. | Contractor will continue to work on punch list items and project will begin close out process with IDOT.
3, 4, 6 | Northmoor - Sheridan Intersection (Stage 1) | Construct the intersection of Northmoor and Sheridan with new lanes and traffic signals, and sidewalks. 70% of the construction to be paid with Federal STP-U funds and City and County to split the costs of the local share of construction and the ROW and engineering costs. | 3382000 | Scott Reeise | IAWC installed new water main north of Northmoor on Sheridan Road and City's contractor completed the south side of Northmoor west of Sheridan. | The contractor will work on the west side of Sheridan Road and the north side of Northmoor Road.
4, 5 | Northmoor - Sheridan to University (Stage 2) | Construct Northmoor with three lanes, curbs, and sidewalks/bike paths between Sheridan and University. This project is funded 70% Federal STP-U funds with the City and County splitting the remainder equally. | 2835000 | Scott Reeise | Working with AmerenCilco to relocated their overhead utilities to allow for the placement of a lighting system. | Will continue working with AmerenCilco and solidify ROW needs so negotiations can begin.
5 | Pioneer Road / Industrial Road | Concrete Joint Repair on Pioneer and Industrial Road. | 450000 | Scott Reeise | Communication to City Council to re-direct these funds to Glen/University Improvement was approved. | N/A
5 | Safer School Sidewalks - Charter Oak | Install new sidewalks by Charter Oak School on Orange Prairie and Timberedge Drive. | 100000 | Scott Reeise | The agreement to final quantities was signed and project closed. | N/A
Varies | 2010 Drainage Projects | Includes projects at 504 E Paris, 6008 N Devonshire, 6322 N Robinwood, 3204 W Parkridge, 1707 W Gilbert, and 2714 W Parkridge | 635000 | Scott Reeise | Final payment was made and the contract was closed. | N/A
Varies | 2011 Drainage Repair Contract | Various | 400000 | Scott Reeise | Contractor installed dry wells to correct a drainage problem at Trewyn School. | Contractor will work on ongoing list of drainage problems throughout the City.
1 | Kumpf/Jefferson Intersection | This project will improve the pedestrian crossing and make this intersection more accessible | 43000 | Nick Stoffer | Contract was awarded to Horowitz Concrete on May 24, 2011. | Contractor should complete the work in September.
5 | Alta/Radnor Intersection | This project will construct the intersection of Radnor Rd and Alta Rd. A roundabout will be considered in the preliminary design phase | 700000 | Scott Reeise | Maurer Stutz has continued with project development engineering. | Consultant is moving forward with completing the design report so that ROW acquisition process can begin. Construction is anticipated in 2012.
1 | US 24/Washington Street | Conduct Phase 1 preliminary design for this route between I-474 and I-74 | 2000000 | Jeff Smith | Followup report on the Concept plan presention in July was made to Council on August 23. Council directed moving forward with engineering and construction on section from Harrison to Maple. | An agreement for final design Of section form Harrison to Maple will be negotiated with Hanson Professional Services, Inc. and presented to Council on Sep 13. An amendment to the IDOT agreement will be presented to Council on Sep 13. Work will continue on the Preliminary Design Report.
2, 3 | Glen and University | State Capital Bill grant for $700,000 to work on Infrastructure in Representative Leitch's district | 1890000 | Scott Reeise | Bid opening held on June 16th . R A Cullinan low bidder. Construction started in July with a change order going to City Council in August to address the pavement issues. | All the work on the outside lanes (curb and gutter, sidewalk, driveways, and landscaping) should be completed by early September. New medians and traffic signals should be completed by end of September.
5 | DCEO Grant | Orange Prairie Road | 350000 | Jeff Smith | DCEO was requested to close the grant | DCEO will close out the grant.
3,4 | DCEO Grant | ICC Traffic signal on University Avenue | 130000 | Jeff Smith | Quarterly report was done and funds were requested and received. | Funds will be transferred to ICC.
1 | DECO Infrastructure Grant | State Capital Bill grants for $100,000 to work on Infrastructure in Representative Gordon's district | 100000 | Jeff Smith | This work is for Harrison Impact Zone sidewalk. Initial $25,000 payment has been received. Grant modification was approved. The quarterly report for August was submitted. | Design will continue and project should be bid in Sep.
5 | Wilhelm Bridge | Construct a bridge on Wilhelm Road between Allen Road and Radnor Road | 2700000 | Scott Reeise | Council award contract on June 14, 2011 to Stark Excavating. County approved the bond sale on July 14. Approval of ROW payment agreement was made July 26. Preconstruction conference was held. Construction contract was signed in mid-August. Contractor started removing trees. | Contractor will begin major construction on the bridge in September.
1 | Warehouse District Tiger II Grant | This grant will assist in building public infrastructure to support the redevelopment of the Warehouse District. | 10000000 | Jeff Smith | Engineer has completed work on survey and much of the work for vaults and façade investigation, environmental, traffic. FHWA approved the categorical class II exclusion. Property owner interviews have been ongoing. First quarterly report was done. Open house was held on Aug 31 at O'Brien Field. | Phase I engineering work will continue. Schedule will be to have the draft Phase 1 study done in October and finalized by Dec 31, 2011.
5 | Allen and Hickory Grove Intersection | Improve intersection in conjunction with the construction of a new Dunlap School. Construction anticipated in 2012. | Funded by Dunlap School District $1.3 M | Nick Stoffer | City-Dunlap School District agreement for ROW was passed by School Board and City Council. | Design and ROW acquisition will proceed.