## Capital Projects Report
| CAPITAL PROJECTS REPORT |  | 2011-08-01 |  | Prepared By Public Works Department - Engineering Division
Primary Council District | Project | Scope | Budget | Contact | Previous Month Activities | Next Month's Planned Activities
4 | Hollyhedges/Deveraux Drainage | Widen the channel of a stream and stabilize the streambank | 1590335 | Scott Reeise | Consultant worked on the Letter of Map Revisions (LOMR) with FEMA | Continue working on the Letter of Map Revisions (LOMR) with FEMA.
N/A | Combined Sewer Overflows | Complete the Long Term Control Plan for the Combined Sewer area | TBD | Jane Gerdes | Continued negotiations. | Continue negotiations.
5 | Pioneer Parkway | Compete an environmental and preliminary design study for Pioneer Parkway between Knoxville and Trigger Rd | TBD | Jane Gerdes | Address review comments. | Address review comments.
5 | Radnor Road RR Xing | Reconstruct Radnor RR Xing per ICC order | 85000 | Scott Reeise | Reviewed agreement with Pioneer Rail regarding crossings at Pioneer Parkway and Radnor Road | Prepare Request for Proposals to design and build the crossings at Pioneer Parkway and Radnor Road
2 | Avalon Place Lighting | Special Assessment project to install ornamental lighting on Avalon Place from Forrest Hill to Hudson | Special Assessment Program | Mike Taylor | Plans and specifications have been advertised and a bid opening will be held August 16th. | Construction set to begin in September.
4 | Easton Place Sidewalk/Road | A Special Assessment project to construct new curbs on both sides and overlay the street and install new sidewalk on the west side. | Special Assessment Program | Scott Reeise | Construction 95% complete. | Contractor will work on punch list items and close project out in August.
All | GPSD/Wildcat Sewers | Sanitary Sewer laterals serving multiple properties before connecting to the public sanitary sewer system | 28000 | Mike Taylor | Worked with the GPSD on problems near Glen Oak School. | Continue working with GPSD on problems as they occur.
3 | Pennsylvania Ave | Remove and replace the pavement on Pennsylvania Ave. from Berkeley Ave. to Glen Oak Ave. Includes ornamental lighting and a new storm sewer system. The intersection of Glen Oak and New York/Wayne St. will be configured as a round-a-bout. Armstrong Ave. will be closed at New York. | 750000 | Scott Reeise | Continued with ROW negotiations. 2 properties remaining to settle. | Continue working on acquiring final pieces of ROW. Complete final review, have IDOT approval, and have a bid letting in early 2012. Construction scheduled to begin in early 2012. Will need to come to agreement on OSF properties and negotiate the elimination of access for 607 NE Armstrong Avenue prior to being advertised for a bid opening. Also need agreement on property at 801 NE Glen Oak prior to being cleared for a letting.
4 | Ridge Road Sidewalks and Lighting | Special Assessment Project to install lighting and sidewalks on Ridge Road from Sheridan to Isabell Ave | 825000 | Mike Taylor | Plans and specifications have been advertised and a bid opening will be held August 16th. | Construction set to begin in September and will carry over into 2012.
3 | Glen Oak Sidewalks Phase III | Replace deteriorated sidewalks to improve walking routes within the Glen Oak Impact Zone. | 200000 | Nick Stoffer | Ordaz is the contractor. Construction is approximately 95% complete. | Construction to wrap up mid August
3 | Glen Oak Sidewalks Phase IV (Durbin Grant) | Replace deteriorated sidewalks to improve walking routes within the Glen Oak Impact Zone. | 120000 | Nick Stoffer | Era Valdivia is the contractor. Construction is 99% complete. | Construction done, a few punch list items to be complete by mid August.
5 | Safer Neighborhood Sidewalks - Keller | Install new sidewalks within 3 blocks of school property to provide safe routes to school for students. | 175000 | Nick Stoffer | Horowitz is the contractor. Construction on Grand next to Washington School is complete. Construction started on Mt. Hawley next to Kellar School and will be complete in August. | Construction to continue through August.
1, 3 | Safer Neighborhood Sidewalks - Trewyn/Washington | Install new sidewalks within 3 blocks of school property to provide safe routes to school for students. | 200000 | Nick Stoffer | Combined with other project. | Washington project to be combined with the Kellar project as the Safer Neighborhood Sidewalk Program. Trewyn project to be removed as a stand alone CIP request for 2012, due to project complexity. Minor drainage improvements are being planned in conjunction with Unit 150 schools.
1 | Safer Neighborhood Sidewalks - Harrison | Install new sidewalks within 3 blocks of school property to provide safe routes to school for students. | 200000 | Steve Austin | Council award contract on June 14, 2011 to Lorusso Cement Contractors. Construction started mid July. Construction approximately 30% complete. | Contractor to continue working on sidewalk, approach and curb work. Construction should be complete around the end of August.
All | Sidewalk Participation 2011 | Upgrade sidewalks within the City to create safe and attractive walking routes. | 385000 | Nick Stoffer | Construction began in April with C&G Concrete as the contractor. All project funds encumbered as of the end of June. Participation fund received added to the budget in late July and immediately encumbered with received applications. | Construction to continue to completion of encumbered funds.
All | Bridge Structure Repairs |  | 30000 | Nick Stoffer | None. | Hire testing company to take concrete core samples in July.
2 | Bridge Inspections | Inspect the Sheridan Rd and Nebraska Ave bridges in preparation of their replacement | 70000 | Nick Stoffer | None. | Request for proposals developed for inspection contracts in September.
2 | Sidewalks In Need of Repair 38 - 2011 | To maintain a safe walking surface for the citizens of Peoria. | 250000 | Nick Stoffer | Bid opening held June 26, 2011. Ordaz apparent low bidder. Contract documents signed. | Construction to begin in mid August.
2 | Main Street | Restripe Main Street between Glendale and Sheridan per HSIP grant. Additionally, to restripe between University and Sheridan using City funds. | HSIP grant $43,642 ($4849 local match). No budget for additional work | Nick Stoffer | Local agency agreement signed by City and submitted to IDOT. Agreement signed by IDOT. | Plans and day labor documents submitted to IDOT for approval. Construction to begin once IDOT approves plans and day labor estimates.
5 | Orange Prairie Rt. 150 to Alta Ln. | Design and construct Orange Prairie Road from Rt. 150 to Rt. 91 | 15000000 | Nick Stoffer | ROW acquisition was completed. IDOT approved the plans for Phase 1 project. Project was advertised for bid to be opened on August 11. | Bid opening will be Aug 11 and Council award is scheduled for Aug 23. Construction will commence in September and carry into mid 2012.
1 | Downtown Arterial Streets | Overlay downtown streets and address pedestrian safety concerns | 550000 | Scott Reeise | No work has been started on this project to date. | Construction funds delayed until 2012. Coordination with Washington St design work will be required.
3, 4, 5 | Northmoor - Knoxville to Sheridan (Stage 3) | Construct Northmoor with three lanes, curbs, and sidewalks/bike paths between Knoxville and Sheridan. This is an ARRA Stimulus Project | 2391543 | Scott Reeise | Contractor will work on punch list items and project will begin close out process with IDOT. | Contractor will continue to work on punch list items and project will begin close out process with IDOT.
3, 4, 6 | Northmoor - Sheridan Intersection (Stage 1) | Construct the intersection of Northmoor and Sheridan with new lanes and traffic signals, and sidewalks. 70% of the construction to be paid with Federal STP-U funds and City and County to split the costs of the local share of construction and the ROW and engineering costs. | 3382000 | Scott Reeise | The contractor worked to complete the storm sewer and all concrete work on the east side of Sheridan and the south side of Northmoor. Traffic was switched to the east side of Sheridan, with the traffic pattern remaining the same. | The contractor will work on the south side of Northmoor between Briarwood and Sheridan constructing curb and gutter, sidewalk and pavement.
4, 5 | Northmoor - Sheridan to University (Stage 2) | Construct Northmoor with three lanes, curbs, and sidewalks/bike paths between Sheridan and University. This project is funded 70% Federal STP-U funds with the City and County splitting the remainder equally. | 2835000 | Scott Reeise | AT&T located their duct bank to not delay this project any further in order to make right of way determinations and prepare plans for an IDOT 2012 fiscal year letting. Revised cost estimate was submitted to PPUATS for additional funding. | Will continue working with AT&T and residents to find a solution to the relocation of a major utility conflict with the project. Will solidify the amount of ROW needed to construct this portion so the appraisal and negotiation process can begin.
5 | Pioneer Road / Industrial Road | Concrete Joint Repair on Pioneer and Industrial Road. | 450000 | Scott Reeise | Communication to City Council to re-direct these funds to Glen/University Improvement was approved. | N/A
5 | Safer School Sidewalks - Charter Oak | Install new sidewalks by Charter Oak School on Orange Prairie and Timberedge Drive. | 100000 | Scott Reeise | The agreement to final quantities was signed and project closed. | N/A
Varies | 2010 Drainage Projects | Includes projects at 504 E Paris, 6008 N Devonshire, 6322 N Robinwood, 3204 W Parkridge, 1707 W Gilbert, and 2714 W Parkridge | 635000 | Scott Reeise | Final payment was made and the contract was closed. | N/A
Varies | 2011 Drainage Repair Contract | Various | 400000 | Scott Reeise | Contractor performed repairs at a City owned parking lot where a sink hole had developed and replacing an old deteriorated corrugated metal pipe on Harmon | Contractor will install dry wells to correct a drainage problem at Trewyn School. Project funds fully encumbered.
1 | Kumpf/Jefferson Intersection | This project will improve the pedestrian crossing and make this intersection more accessible | 43000 | Steve Austin | Project was bid on May 10, 2011. | Contract was awarded to Horowitz Concrete on May 24, 2011 and work should begin in August
5 | Alta/Radnor Intersection | This project will construct the intersection of Radnor Rd and Alta Rd. A roundabout will be considered in the preliminary design phase | 700000 | Scott Reeise | City Council approved moving forward with a roundabout at this location. | Consultant is moving forward with completing the design report so that ROW acquisition process can begin. Construction is anticipated in 2012.
1 | US 24/Washington Street | Conduct Phase 1 preliminary design for this route between I-474 and I-74 | 2000000 | Jeff Smith | Concept plan was presented to Council and the public on July 19. | There will be follow up on Council concerns prepared for Aug 23 Council meeting. An agreement for final design on a selected alternatives will be negotiated with Hanson Professional Services, Inc.
2, 3 | Glen and University | State Capital Bill grant for $700,000 to work on Infrastructure in Representative Leitch's district | 1890000 | Scott Reeise | Bid opening held on June 16th . R A Cullinan low bidder. Construction started in July. | Construction scheduled to be complete by the end of the construction season.
5 | DCEO Grant | Orange Prairie Road | 350000 | Jeff Smith | DCEO was requested to close the grant | DCEO will close out the grant.
3,4 | DCEO Grant | ICC Traffic signal on University Avenue | 130000 | Jeff Smith | Quarterly report was done and funds were requested. | ICC will be contacted to negotiate a maintenance arrangement.
1 | DECO Infrastructure Grant | State Capital Bill grants for $100,000 to work on Infrastructure in Representative Gordon's district | 100000 | Jeff Smith | This work is for Harrison Impact Zone sidewalk. Initial $30,000 payment has been received. Grant modification was approved. | Design will continue and project should be bid in Aug.
5 | Wilhelm Bridge | Construct a bridge on Wilhelm Road between Allen Road and Radnor Road | 2700000 | Scott Reeise | Council award contract on June 14, 2011 to Stark Excavating. County approved the bond sale on July 14. Approval of ROW payment agreement was made July 26. Preconstruction conference was held. | Construction is on hold, waiting for Peoria County to approve the funding mechanism and finalize ROW acquisition.
1 | Warehouse District Tiger II Grant | This grant will assist in building public infrastructure to support the redevelopment of the Warehouse District. | 10000000 | Jeff Smith | Engineer has completed work on survey and much of the work for vaults and façade investigation, environmental, traffic. FHWA approved the categorical class II exclusion. Property owner interviews have been ongoing. First quarterly report was done. | Phase I engineering work will continue. Roadway configuration will be done. Schedule will be to have the draft Phase 1 study done in October and finalized by Dec 31, 2011.
5 | Allen and Hickory Grove Intersection | Improve intersection in conjunction with the construction of a new Dunlap School. Construction anticipated in 2012. | Funded by Dunlap School District $1.3 M | Nick Stoffer | Dunlap School District, Traffic Commission, and City Council have approved a roundabout in lieu of a traditional intersection. Design and ROW acquisition has progressed | City-Dunlap School District agreement for ROW will be proposed on Aug 9 Council meeting. Public meeting will be held later in the year and public information will be developed. Schedule for construction early spring 2012.